## Project Tracker
Project Tracker
| Percent Over/Under to Flag: | 0%
Project | Phase | Assigned To | Estimated Start | Estimated Finish | Estimated Work (in hours) | Actual Start | Actual Finish | Actual Duration (in days) | Notes | Status
Utility Portal and Database Design | Phase 1 | Amandeep Joshi | 2018-12-23 | 2019-01-15 | 15 | 2018-12-23 |  |  |  | In Progress
DEM switching circuit Design | Phase 1 | Amandeep Joshi | 2018-12-23 | 2019-01-06 | 5 | 2018-12-30 | 2019-01-04 | 4 |  | completed
CCU and User Interface Design | Phase 1 | Damilola Oludiran | 2018-12-23 | 2019-01-15 | 30 | 2018-12-23 |  |  |  | In Progress
DEM Power Supply and CT Design and Testing | Phase 1 | Bikramjit Saini | 2018-12-26 | 2019-01-18 | 35 | 2018-12-26 |  |  |  | In Progress
Zigbee Communications Design | Phase 1 | Damilola Oludiran | 2019-01-09 | 2019-01-21 | 40
Thermostat System Design | Phase 1 | Amandeep Joshi | 2019-01-10 | 2019-01-21 | 25
DEM Logic board design | Phase 1 | Bikramjit Saini | 2019-01-09 | 2019-01-21 | 30
CCU Enclosure Design | Phase 2 | Damilola Oludiran | 2019-01-21 | 2019-02-04 | 10
DEM Enclosure Design | Phase 2 | Bikramjit Saini | 2019-01-21 | 2019-02-04 | 10
CCU testing | Phase 2 | Damilola Oludiran | 2019-01-15 | 2019-01-16 | 4
Utilility Portal testing | Phase 2 | Amandeep Joshi | 2019-01-15 | 2019-01-16 | 4
Thermostat System testing | Phase 2 | Amandeep Joshi | 2019-01-22 | 2019-01-22 | 4
DEM switching circuit Testing | Phase 2 | Amandeep Joshi | 2019-01-23 | 2019-01-23 | 10
Utility Portal and CCU integration | Phase 2 | Amandeep, Dami | 2019-01-16 | 2019-01-17 | 5
Wireless Communication testing (Zgbee) | Phase 2 | Bikramjit,Dami | 2019-01-22 | 2019-01-23 | 5
DEM Electronic system testing | Phase 2 | Amandeep, Bikramjit | 2019-01-25 | 2019-01-28 | 10
SETUP

## Setup
Setup
Phase | Team Member | Status
Phase 1 | Amandeep Joshi | In Progress
Phase 2 | Bikramjit Saini | Completed
Phase 3 | Damilola Oludiran | overdue
Amandeep, Dami
Bikramjit,Dami
Amandeep, Bikramjit
PROJECTS